## Sample Project (hidden)
Task | Supporting Task | Time Estimated | Time Actual
Article - PDF | Review sm&r and write 1st draft. | 0.5
Animation_Video | Review storyboard. | 0.25

## Fin Tech
Start Date | Task | Supporting Task | Time Estimated | Time Actual |  | Notes
2020-04-27 | Topic Kick Off / Admin Set Up | Kick off meeting | 0.25
2020-04-27 | Topic Kick Off / Admin Set Up | Create topic specifications document | 0.25
2020-04-27 | Topic Kick Off / Admin Set Up | Create questions & objectives document | 0.25
2020-04-28 | Topic Kick Off / Admin Set Up | Review & sign off questions & objectives documents | 0.25
2020-04-28 | Intro_Video_SME | Review sm&r and write 1st draft. | 0.25
2020-04-28 | Intro_Video_SME | SME 1st draft review and edits + Table read | 0.25
2020-04-29 | Intro_Video_SME | SME 1st draft review and edits + Table read | 0.25
2020-04-29 | Intro_Video_SME | Kick off / Brief vendor | 0.25
2020-04-29 | How-To Video (SME) | Video shoot | 0.25
2020-04-30 | Intro_Video_SME | Review 1st cut | 0.25
2020-04-30 | Intro_Video_SME | Review final video | 0.5
2020-05-01 | Intro_Video_SME | Sign off | 0.25
2020-09-15 | Intro_Video_SME | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #1
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| How-To Video (SME) | Review sm&r and write 1st draft. | 0.5 |  |  | How to Vid #1
| How-To Video (SME) | SME 1st draft review and edits + Table read | 0.25
| How-To Video (SME) | Kick off / Brief vendor | 0.25
| How-To Video (SME) | Video shoot | 0.5
| How-To Video (SME) | Review 1st cut | 0.25
| How-To Video (SME) | Review final video | 0.25
| How-To Video (SME) | Sign off | 0.25
| How-To Video (SME) | Handover asset. | 0.25
| How-To Video (SME) | Review sm&r and write 1st draft. | 0.5 |  |  | How to Vid #2
| How-To Video (SME) | SME 1st draft review and edits + Table read | 0.25
| How-To Video (SME) | Kick off / Brief vendor | 0.25
| How-To Video (SME) | Video shoot | 0.5
| How-To Video (SME) | Review 1st cut | 0.25
| How-To Video (SME) | Review final video | 0.25
| How-To Video (SME) | Sign off | 0.25
| How-To Video (SME) | Handover asset. | 0.25
| Animation_Video | Review source material and references and write script. | 0.5
| Animation_Video | SME script review and edits. | 0.25
| Animation_Video | Brief animator / vendor. | 0.25
| Animation_Video | Review storyboard. | 0.25
| Animation_Video | Review first cut. | 0.25
| Animation_Video | Review final cut and handover thumbnail. | 0.25
| Animation_Video | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #2
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #3
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | FAQ (using Gomo Article format/timing)
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - PDF | Review sm&r and write 1st draft. | 0.5 |  |  | Job Aid (using PDF Article format/timing)
| Article - PDF | SME 1st draft review and edits. | 0.25
| Article - PDF | Brief GD. | 0.25
| Article - PDF | Review 1st draft of final product. | 0.25
| Article - PDF | Review final article | 0.25
| Article - PDF | Handover asset. | 0.25
| Podcast | Review sm&r and write 1st draft. | 0.5 |  |  | Podcast (timing still TBD on costing doc)
| Knowledge Check LMS | Review draft questions, options and feedback | 0.25
| Knowledge Check LMS | Create MCQ CSV + Upload to appropriate folder | 0.25
| Knowledge Check LMS | Handover asset. | 0.25 |  | Total Days:
(assuming 8 hours=1 day)
24.5

## Behavioral Eco
Start Date | Task | Supporting Task | Time Estimated | Time Actual |  | Notes
2020-04-27 | Article - PDF | Kick off meeting | 0.25
2020-04-27 | Topic Kick Off / Admin Set Up | Create topic specifications document | 0.25
2020-04-27 | Topic Kick Off / Admin Set Up | Create questions & objectives document | 0.25
2020-04-28 | Topic Kick Off / Admin Set Up | Review & sign off questions & objectives documents | 0.25
2020-04-28 | Intro_Video_SME | Review sm&r and write 1st draft. | 0.25
2020-04-28 | Intro_Video_SME | SME 1st draft review and edits + Table read | 0.25
2020-04-29 | Intro_Video_SME | SME 1st draft review and edits + Table read | 0.25
2020-04-29 | Intro_Video_SME | Kick off / Brief vendor | 0.25
2020-04-29 | How-To Video (SME) | Video shoot | 0.25
2020-04-30 | Intro_Video_SME | Review 1st cut | 0.25
2020-04-30 | Intro_Video_SME | Review final video | 0.5
2020-05-01 | Intro_Video_SME | Sign off | 0.25
| Intro_Video_SME | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #1
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| How-To Video (SME) | Review sm&r and write 1st draft. | 0.5 |  |  | How to Vid #1
| How-To Video (SME) | SME 1st draft review and edits + Table read | 0.25
| How-To Video (SME) | Kick off / Brief vendor | 0.25
| How-To Video (SME) | Video shoot | 0.5
| How-To Video (SME) | Review 1st cut | 0.25
| How-To Video (SME) | Review final video | 0.25
| How-To Video (SME) | Sign off | 0.25
| How-To Video (SME) | Handover asset. | 0.25
| How-To Video (SME) | Review sm&r and write 1st draft. | 0.5 |  |  | How to Vid #2
| How-To Video (SME) | SME 1st draft review and edits + Table read | 0.25
| How-To Video (SME) | Kick off / Brief vendor | 0.25
| How-To Video (SME) | Video shoot | 0.5
| How-To Video (SME) | Review 1st cut | 0.25
| How-To Video (SME) | Review final video | 0.25
| How-To Video (SME) | Sign off | 0.25
| How-To Video (SME) | Handover asset. | 0.25
| Animation_Video | Review source material and references and write script. | 0.5
| Animation_Video | SME script review and edits. | 0.25
| Animation_Video | Brief animator / vendor. | 0.25
| Animation_Video | Review storyboard. | 0.25
| Animation_Video | Review first cut. | 0.25
| Animation_Video | Review final cut and handover thumbnail. | 0.25
| Animation_Video | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #2
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | Article #3
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - Gomo | Review sm&r and write 1st draft. | 0.5 |  |  | FAQ (using Gomo Article format/timing)
| Article - Gomo | SME reviews 1st draft and edits. | 0.25
| Article - Gomo | Brief GD. | 0.25
| Article - Gomo | Review graphics | 0.25
| Article - Gomo | Create 1st draft GOMO article | 0.5
| Article - Gomo | Review 1st draft | 0.25
| Article - Gomo | Create final GOMO article | 0.25
| Article - Gomo | Review final GOMO article | 0.25
| Article - Gomo | Handover asset. | 0.25
| Article - PDF | Review sm&r and write 1st draft. | 0.5 |  |  | Job Aid (using PDF Article format/timing)
| Article - PDF | SME 1st draft review and edits. | 0.25
| Article - PDF | Brief GD. | 0.25
| Article - PDF | Review 1st draft of final product. | 0.25
| Article - PDF | Review final article | 0.25
| Article - PDF | Handover asset. | 0.25
| Podcast | Review sm&r and write 1st draft. | 0.5 |  |  | Podcast (timing still TBD on costing doc)
| Knowledge Check LMS | Review draft questions, options and feedback | 0.25
| Knowledge Check LMS | Create MCQ CSV + Upload to appropriate folder | 0.25
| Knowledge Check LMS | Handover asset. | 0.25 |  | Total Days:
(assuming 8 hours=1 day)
24.5

## Weekly Capcity Preview
Jono | Project Time (in Days) | Non-Project Time (in Days) | Total Weekly Time (in Days) | Total Weekly Time in Hours | Weekly Hours Available
Project #1
Project #2
Project #3
Luke
Project #1 | #REF!
Project #2
Project #3
Ashley
Fin Tech | 3.25 | 0.63 | 7.13 | 57.04 | 36
Behavioral Economics | 3.25
Project #3
Mac
Project #1
Project #2
Project #3
Ali
Project #1
Project #2
Project #3

## Allocation
Team Member | Role | % Allocation | Hours/day | Hours / Week
Jono | Head of Learning | 90% | 7.2 | 36
Luke | Production Manager | 90% | 7.2 | 36
Ashley | Instructional Designer | 90% | 7.2 | 36
Mac | Instructional Designer | 50% | 4 | 20
Ali | Project Manager | 30% | 2.4 | 12
SME
Copywriter
|  |  | Daily Default Working Hours | 8
Focus Factor: 10% deducted from all team members for unplanned taks.

## Non-Project Time -AK
Date | Non-Project Time | Supporting Task | Time Estimated | Time Actual |  | Notes
2020-04-27 | Meeting: Monday LPD Team Check In | Meeting | 0.06
2020-04-27 | Meeting: Check-in Core Learn Team | Meeting | 0.06
2020-04-30 | Meeting: Weekly KPA Learning Team | Meeting | 0.13
2020-04-30 | Meeting: US ID Weekly | Meeting | 0.13
| Meeting: Fortnightly 121 | Meeting
2020-04-30 | Meeting: Fortnightly 121 | Meeting | 0.13 |  |  | Using as placeholder for 121 w/ Susan
2020-04-28 | Meeting: Misc |  | 0.06
2020-05-01 | Meeting: Friday LPD Team Virtual Bar |  | 0.06 |  | Total Days:
0.63
|  |  | Total Days: | 0.63
(assuming 8 hours=1 day)

## Tasks and Time Categories
Animation_Video |  | Article - Gomo |  | Article - PDF |  | How-To Video (SME) |  | Intro_Video_SME |  | Knowledge Check - Gomo |  | Knowledge Check LMS |  | Topic Kick Off / Admin Set Up |  | Meeting: Friday LPD Team Virtual Bar |  | Meeting: Check-in Core Learn Team |  | Meeting: Fortnightly 121 |  | Meeting: Weekly KPA Learning Team |  | Meeting: Misc |  | Meeting: Monday LPD Team Check In |  | Meeting: US ID Weekly |  | Meeting: Weekly Team Check In |  | Planning and Scoping |  | Podcast |  | Topic Kick Off / Admin Set Up |  | Holiday |  | PTO |  | OOO
Provide source material and references. | 0.25 | Provide source material and references. | 0.5 | Provide source material and references. | 0.5 | Provide source material and references. | 0.5 | Provide source material and references. | 0.25 | Write draft questions, options and feedback | 0.25 | Write draft MCQ questions, options and feedback | 0.25 | Kick off meeting | 0.25 | Meeting | 0.13 | Meeting | 0.06 | Meeting | 0.06 | Meeting | 0.13 | Meeting | 0.13 | Meeting | 0.06 | Meeting | 0.13 | Meeting | 0.13 | Meeting | 0.13 | Provide source material and references. | 0.5 | Meeting | 0.25 | Public Holiday | 1 | Paid Time Off | 1 | Out of Office | 1
Review source material and references and write script. | 0.5 | Review sm&r and write 1st draft. | 0.5 | Review sm&r and write 1st draft. | 0.5 | Review sm&r and write 1st draft. | 0.5 | Review sm&r and write 1st draft. | 0.25 | Review draft questions, options and feedback | 0.25 | Review draft questions, options and feedback | 0.25 | Create topic specifications document | 0.25 | [18 empty] | Review sm&r and write 1st draft. | 0.5
SME script review and edits. | 0.25 | SME reviews 1st draft and edits. | 0.25 | SME 1st draft review and edits. | 0.25 | SME 1st draft review and edits + Table read | 0.25 | SME 1st draft review and edits + Table read | 0.25 | Create 1st draft Knowledge Check | 0.25 | Create MCQ CSV + Upload to appropriate folder | 0.25 | Create questions & objectives document | 0.25
Brief animator / vendor. | 0.25 | Proofread and copy edit. | 0.25 | Proofread and copy edit. | 0.25 | Proofread and copy edit. | 0.25 | Kick off / Brief vendor | 0.25 | Review 1st draft | 0.25 | Proof read Knowledge check | 0.25 | Review & sign off questions & objectives documents | 0.25
Review storyboard. | 0.25 | Brief GD. | 0.25 | Brief GD. | 0.25 | Kick off / Brief vendor | 0.25 | Video shoot | 0.5 | Proof read Knowledge check | 0.25 | Handover asset. | 0.25
Proofread and copy edit. | 0.25 | Design / curate artwork | 1 | Design artwork and create final product. | 1 | Video shoot | 0.5 | Review 1st cut | 0.25 | Create final GOMO Knowledge check | 0.25
Review first cut. | 0.25 | Review graphics | 0.25 | Review 1st draft of final product. | 0.25 | Review 1st cut | 0.25 | Review final video | 0.25 | Handover asset. | 0.25
Review final cut and handover thumbnail. | 0.25 | Amend final graphics | 0.25 | Create final article | 0.25 | Review final video | 0.25 | Sign off | 0.25
Handover asset. | 0.25 | Create 1st draft GOMO article | 0.5 | Review final article | 0.25 | Sign off | 0.25 | Handover asset. | 0.25
|  | Review 1st draft | 0.25 | Handover asset. | 0.25 | Handover asset. | 0.25
|  | Create final GOMO article | 0.25
|  | Review final GOMO article | 0.25
|  | Handover asset. | 0.25

## Time in Days
Time in Days
0.06
0.13
0.25
0.5
1

## About and Instructions
How the Capacity Preview Works: Each team member lists their current projects under their name in column A. Project Time (column C) is pulled from the total for each corresponding project using the SUm function i.e. =SUM('Copy of Behavioral Eco'!F85. Non-Project time is tracked in the same way. Total weekly time Column E is calculated using the following formula: =SUM(C10:C11)+(D10) which adds the numbers of project and non-project time. Weekly Hours Available pulls data from the Allocation sheet. How the Allocation Sheet Works: A daily default of 8 hours is set in E13. Column C indicates the capacity for each team member minus a focus factor of 10% for unplanned work. So a person who works 3 days a week would have a capacity of 60% minus a focus factor of 10% meaning that this column will show 50% as their total capacity. Column D calculates daily hours available using the following formula: =$E$13*C2 (the second half is updated for each person). Column D uses the formula =D2*5 to show the hours available each week (the second half is updated for each person). How the Project Sheets Work: Each project sheet includes dependent drop-downs that allow the user to select a Primary Task i.e. "Intro Video." This user input will then inform what is visible in the second drop down menu which includes secondary tasks i.e. "Review sm&r and write 1st draft." Secondary tasks have a time value associated with them which autopoluates in the next cell. This is handled in the script editor (accessible on the main menu via Tools>Script Editor). All primary tasks, secondary tasks and corresponding time estimates are listed in the Tasks and Time Categories tab. Time in days is listed in another tab. This data served into the scripts. Utilizing a dependent drop down alleviates the need to type out tasks, timing, etc. It also enables the user to plan ahead according to process based tasks. For example, the user can add future dates and then populate the rows with each corresponding task. Once the task is completed the end user can add in actual time to complete the task which can be compared with the time estimate. Non-Project sheets work in the same manner, however, they track meetings, PTO, etc. *Time is being tacked in days to match other KPA standards, however, hourly tracking would be more accurate. Instructions: Make a copy of one of the sample projects. Name the project and add your initials. Using column “B” add in primary tasks for the project as they relate to your role. This will trigger the drop down menu in column “C” to update. Select the supporting tasks in column “C” that relate to your role. Timing will auto populate under “Estimate.” If additional tasks need to be added this can be done on the “Tasks” tab.